## WBS Input
Project WBS |  |  | Ver.0.1
2026-04-21
Phase | ID | Task Name | Details | Owner | Planned Start | Planned End | Actual Start | Actual End | Status | Notes for Task Dependency | Notes
1. Planning & Current State Analysis
| 1.1 | Current Operations Inventory | Define scope of target business operations | Alice | 2026-04-01 | 2026-05-01 | 2026-04-01 |  | In Progress | None (project kickoff task)
| 1.1.1 | Revise Current Business Process Flowcharts | Update and visualize payroll, social insurance, and attendance processes | Alice | 2026-04-01 | 2026-05-01 | 2026-04-03 |  | In Progress | Depends on 1.1 (scope must be defined first) | Manage the full process flowchart revision (1.1.1) and individual operations inventory sheets (1.1.5 onward) as separate deliverables (suited for large projects). Alternatively, organize by business area within the flowchart revision (suited for small to mid-size projects).
| 1.1.2 | Review Current SLA & Performance Evaluation | Identify current vendor performance gaps and unmet items | Bob | 2026-04-01 | 2026-04-15 |  |  | Not Started | Depends on 1.1 (scope must be defined first)
| 1.1.3 | Create RACI Responsibility Matrix | Clarify responsibilities among internal HR, IT, and current vendor | [6 empty] | Depends on 1.1.1, 1.1.2 (requires process & SLA understanding)
| 1.1.4 | Identify Exception & Non-Standard Processes | Identify undocumented special handling procedures | [6 empty] | Depends on 1.1.1 (exceptions identified during flowchart revision)
| 1.1.5 | Review Social Insurance & Labor Insurance Operations | Map health insurance and pension enrollment/disenrollment, standard remuneration, and monthly changes | [6 empty] | Depends on 1.1 (scope must be defined first) | Add individual outsourced operations from 1.1.5 onward
| 1.1.6 | Review Resignation & Leave of Absence Procedures | Visualize severance pay calculations, separation certificates, parental/sick leave benefits | [6 empty] | Depends on 1.1 (scope must be defined first)
| 1.1.7 | Review Benefits-Related Administrative Tasks | Organize allowances, ESOP, savings plans, health check booking coordination, etc. | [6 empty] | Depends on 1.1 (scope must be defined first)
| 1.1.8 | Review Year-End Tax Adjustment Processes | Identify year-end adjustment schedule, filing systems, and e-filing usage | [6 empty] | Depends on 1.1 (scope must be defined first)
| 1.1.9 | abcdef | aaaaaa
| 1.1.10 | ghijk | bbbbbb
| 1.3 | Budget & Schedule Planning | Obtain approval for project execution plan | [6 empty] | Depends on 1.1 (cost/schedule based on inventory findings)
| 1.3.1 | Estimate Transition Costs | Compare initial implementation costs vs. ongoing operating costs | [6 empty] | Depends on 1.1 (cost estimation requires scope clarity)
| 1.3.2 | Create Project Roadmap | Create timeline from RFP issuance through go-live | [6 empty] | Depends on 1.1.8 (timeline shaped by all inventory tasks)
| 1.3.3 | Develop Resource Plan | Secure internal team capacity and establish project structure | [6 empty] | Depends on 1.3.1, 1.3.2 (resource needs follow cost & timeline)
2. Vendor Selection
| 2.1 | Prepare & Send RFI/RFP | Distribute RFP and manage Q&A process | [6 empty] | Depends on 1.3 (budget & schedule must be approved)
| 2.2 | Evaluate Proposals & Select Vendor | Conduct presentations and score-based selection | [6 empty] | Depends on 2.1 (proposals received before evaluation)
3. Transition Preparation (Design)
| 3.1 | Design To-Be Business Processes | Optimize operations under new vendor structure | [6 empty] | Depends on 2.2 (vendor selected before designing To-Be)
| 3.1.1 | Gap Analysis of Business Processes | Identify gaps between current and new vendor standard capabilities | [6 empty] | Depends on 1.1.1, 2.2 (compare As-Is vs. vendor capabilities)
| 3.1.2 | Redesign Approval Workflows | Configure approval routes and HRIS permissions | [6 empty] | Depends on 3.1.1 (gap analysis informs workflow redesign)
| 3.2 | System/Data Integration Design | Ensure data integrity | [6 empty] | Depends on 3.1 (process design drives integration needs)
| 3.2.1 | Create Interface Specifications | Define integration points with HCM, payroll systems, etc. | [6 empty] | Depends on 3.1, 3.2 (interface specs follow process & data design)
| 3.2.2 | Master Data Mapping | Reconcile organization codes, names, and attribute definitions | [6 empty] | Depends on 3.1.1 (data mapping requires gap analysis results)
| 3.3 | Develop Migration Plan | Minimize transition risks | [6 empty] | Depends on 3.1, 3.2 (migration plan requires process & data design)
| 3.3.1 | Data Cleansing Plan | Identify HR data requiring correction before migration | [6 empty] | Depends on 3.2.2 (cleansing targets identified from data mapping)
| 3.3.2 | Parallel Run Plan | Define payroll dual-verification period and test population | [6 empty] | Depends on 3.3.1 (parallel run plan follows data cleansing plan)
4. Build & Test
| 4.1 | User Acceptance Testing (UAT) | Operational testing based on business scenarios | [6 empty] | Depends on 3.1, 3.2, 3.3 (all design & migration plans must be complete)
5. Migration & Parallel Run
| 5.1 | Execute Parallel Run | Reconcile payroll calculations between current and new vendor | [6 empty] | Depends on 4.1 (UAT must pass before parallel run)
| 5.2 | Go-Live Cutover | Complete transition to new vendor | [6 empty] | Depends on 5.1 (parallel run reconciliation must be verified)
6. ABC
| 6.1 | abcdef | cccccc
| 6.2 | ghijk | dddddd

## WBS Tree View
Project WBS Tree |  | Ver.0.1
2026-04-21
ID | Phase / Task Name | Details | Owner | ステータス
★ | ■ 1. Planning & Current State Analysis
1.1 | ├─ Current Operations Inventory | Define scope of target business operations | Alice | In Progress
1.1.1 | │ ├─ Revise Current Business Process Flowcharts | Update and visualize payroll, social insurance, and attendance processes | Alice | In Progress
1.1.2 | │ ├─ Review Current SLA & Performance Evaluation | Identify current vendor performance gaps and unmet items | Bob | Not Started
1.1.3 | │ ├─ Create RACI Responsibility Matrix | Clarify responsibilities among internal HR, IT, and current vendor
1.1.4 | │ ├─ Identify Exception & Non-Standard Processes | Identify undocumented special handling procedures
1.1.5 | │ ├─ Review Social Insurance & Labor Insurance Operations | Map health insurance and pension enrollment/disenrollment, standard remuneration, and monthly changes
1.1.6 | │ ├─ Review Resignation & Leave of Absence Procedures | Visualize severance pay calculations, separation certificates, parental/sick leave benefits
1.1.7 | │ ├─ Review Benefits-Related Administrative Tasks | Organize allowances, ESOP, savings plans, health check booking coordination, etc.
1.1.8 | │ ├─ Review Year-End Tax Adjustment Processes | Identify year-end adjustment schedule, filing systems, and e-filing usage
1.1.9 | │ ├─ abcdef | aaaaaa
1.1.10 | │ ├─ ghijk | bbbbbb
1.3 | ├─ Budget & Schedule Planning | Obtain approval for project execution plan
1.3.1 | │ ├─ Estimate Transition Costs | Compare initial implementation costs vs. ongoing operating costs
1.3.2 | │ ├─ Create Project Roadmap | Create timeline from RFP issuance through go-live
1.3.3 | │ ├─ Develop Resource Plan | Secure internal team capacity and establish project structure
★ | ■ 2. Vendor Selection
2.1 | ├─ Prepare & Send RFI/RFP | Distribute RFP and manage Q&A process
2.2 | ├─ Evaluate Proposals & Select Vendor | Conduct presentations and score-based selection
★ | ■ 3. Transition Preparation (Design)
3.1 | ├─ Design To-Be Business Processes | Optimize operations under new vendor structure
3.1.1 | │ ├─ Gap Analysis of Business Processes | Identify gaps between current and new vendor standard capabilities
3.1.2 | │ ├─ Redesign Approval Workflows | Configure approval routes and HRIS permissions
3.2 | ├─ System/Data Integration Design | Ensure data integrity
3.2.1 | │ ├─ Create Interface Specifications | Define integration points with HCM, payroll systems, etc.
3.2.2 | │ ├─ Master Data Mapping | Reconcile organization codes, names, and attribute definitions
3.3 | ├─ Develop Migration Plan | Minimize transition risks
3.3.1 | │ ├─ Data Cleansing Plan | Identify HR data requiring correction before migration
3.3.2 | │ ├─ Parallel Run Plan | Define payroll dual-verification period and test population
★ | ■ 4. Build & Test
4.1 | ├─ User Acceptance Testing (UAT) | Operational testing based on business scenarios
★ | ■ 5. Migration & Parallel Run
5.1 | ├─ Execute Parallel Run | Reconcile payroll calculations between current and new vendor
5.2 | ├─ Go-Live Cutover | Complete transition to new vendor
★ | ■ 6. ABC
6.1 | ├─ abcdef | cccccc
6.2 | ├─ ghijk | dddddd

## User Guide
WBS User Guide
■ Sheet Structure
Sheet Name | Purpose | Editing
WBS Input | Data entry and editing. All changes are made here. | ○ Editable
WBS Tree View | Tree-format read-only view. Formulas automatically reference "WBS Input". | ▲ Do not directly edit cells (formulas will break). Adding rows and copying formulas is OK.
User Guide | This sheet. Explains usage and maintenance procedures. | -
■ How to Use the "WBS Input" Sheet
Column Layout:
Column A (Phase) | Enter only the phase name. Example: "1. Planning & Current State Analysis"
Column B (ID) | WBS number. Example: 1.1 / 1.1.1 / 1.3.2
Column C (Task Name) | Name of the task
Column D (Details) | Description/definition of the task
Column K (Notes for Task Dependency) | Notes or comments related to task dependencies
Row Types:
Phase Row | Enter the phase name in column A only. Leave columns B, C, and D blank.
Mid-Level Task Row | Enter ID (one dot) in column B. Example: 1.1 / 2.1 / 3.2
Leaf Task Row | Enter ID (two dots) in column B. Example: 1.1.1 / 3.2.2
Important Rules:
1 | Phase rows: only fill column A. Do not enter data in columns B, C, or D.
2 | Task rows: leave column A blank and start entering from column B.
3 | Place tasks directly below their phase (the order is reflected in the tree view).
■ Maintenance Procedures
Action | WBS Input Sheet | WBS Tree View
Change task name/details | Edit column C or D in WBS Input sheet | Auto-updated. No action needed.
Change ID | Edit column B in WBS Input sheet | Auto-updated. Tree hierarchy adjusts automatically.
Insert task between existing rows | Insert a row in WBS Input sheet and enter data | Auto-updated if within the formula reserve rows. Otherwise, extend formulas per instructions below.
Add task at the end | Add a row at the bottom of WBS Input sheet and enter data | Row addition needed on Tree View side as well. See instructions below.
Add a phase | Add a phase row (column A only) and task rows | Row addition needed on Tree View side as well. See instructions below.
Delete a task | Delete the row in WBS Input sheet | Deleted rows will show #REF! errors. Copy formulas from a non-error row to fix the Tree View.
■ How to Extend Formulas in the WBS Tree View
If WBS Input grows beyond the Tree View's formula reserve rows (whether appending or inserting), you need to extend the formula range on the Tree View side.
Step 1: | Open the WBS Tree View sheet
Step 2: | Select the last row that contains formulas
Step 3: | Select all 3 cells in columns A, B, and C, then drag the fill handle (■) down to the required number of rows
Step 4: | Formulas are copied to the new rows and WBS Input data is displayed automatically
※ If there are enough reserve rows, this step is not needed. The current formula range extends to row 100.
■ How the Tree View Works
Symbol | Level | Detection Logic
■ | Phase | Row where column A (Phase) in WBS Input is not empty
├─ | Mid-Level Task | Column B ID has 1 or fewer dots (e.g., 1.1, 2.1)
│ ├─ | Leaf Task | Column B ID has 2 or more dots (e.g., 1.1.1, 3.2.2)
Formatting:
Phase Row | Blue background + Bold + 11pt (auto-applied via conditional formatting)
Mid-Level Task Row | Bold (auto-applied via conditional formatting)
Leaf Task Row | Normal formatting